## Application
Phase	Sprint	Application	Group	Task	Minimum	Medium	Maximum	Unit	Urgency	Developers	Design Completion	Design Status	Code Completion	Code Status		Notes	Issues
1		Hybrid	Account	Account creation	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
1		Hybrid	Account	Email account connection	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
1		Hybrid	Account	Account profile picture	0	0	0	man-days	5		100%	validated	100%	upcoming
1		Hybrid	About	About	0	0	0	man-days	5		100%	missing	100%	missing			Missing final style
1		Hybrid	Home	Update homepage	0	0	0	man-days	5		100%	evaluated	100%	missing
1		Hybrid	Account	Account overview	0	0	0	man-days	5	Fernando	80%	evaluated	100%	deployed
1		Hybrid	Blog	Blog home	0	0	0	man-days	1	Luís	0%	missing	100%	deployed
1		Hybrid	Blog	Article page	0	0	0	man-days	1	Luís	0%	missing	100%	deployed
1		Hybrid	Account	Account edition	0	0	0	man-days	5	Fernando, Luís	100%	validated	100%	in progress
2		Hybrid	Start	Start	0	0	0	man-days	5		100%	validated	100%	deployed
2		Hybrid	Onboarding	Onboarding type selection	0	0	0	man-days	5		100%	validated	100%	deployed			Load more properties, Finish map features
2		Hybrid	Onboarding	Onboarding short term location	0	0	0	man-days	5		100%	validated	100%	deployed		Used old version desing
2		Hybrid	Onboarding	Onboarding short term calendar	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed		Used old version desing
2		Hybrid	Onboarding	Onboarding short term guest count	0	0	0	man-days	5		100%	validated	100%	deployed
2		Hybrid	Onboarding	Onboarding short term budget	0	0	0	man-days	5		100%	validated	100%	deployed
2		Hybrid	Onboarding	Onboarding short term housing list	0	0	0	man-days	5		100%	validated	100%	deployed		On account creation check if account already exists and missing email template	Doesnt warn when user already exist
2		Hybrid	Housing	Housing description edition	0	0	0	man-days	5		100%	validated	100%	deployed		Email template
2		Hybrid	Housing	Housing equipment list edition	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed		Missing email edition	The way your authentication works does not provide a solution when the user miss the email connection
2		Hybrid	Housing	Housing location edition	0	0	0	man-days	5		100%	validated	100%	deployed		Profile picture bugs on format in menu button and when updating (see card on trello)
2		Hybrid	Housing	Housing short term edition	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
2		Hybrid	Housing	Housing view	0	0	0	man-days	5	Fernando, Fabiano	100%	validated	100%	deployed
2		Hybrid	Housing	Housing description	0	0	0	man-days	1		100%	validated	100%	deployed		Missing features differentiation
2		Hybrid	Housing	Housing summary	0	0	0	man-days	5	Fernando	100%	validated	100%	upcoming		Missing add verification to image upload to only allow the property ad creation uppon the images being properly updated
2		Hybrid	Housing	Housing equipment menu	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
2		Hybrid	Housing	Housing equipment list	0	0	0	man-days	5	Fernando	100%	validated	100%	upcoming
2		Hybrid	Housing	Housing short term rental information	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed		Missing housing rules components, Missing availability component
2		Hybrid	Housing	Housing comment list	0	0	0	man-days	1	Fabiano	100%	validated	100%	deployed
2		Hybrid	Housing	Housing map	0	0	0	man-days	5		100%	validated	100%	deployed		Imo this need to be evaluated
2		Hybrid	Housing	Housing contact	0	0	0	man-days	5		100%	validated	100%	upcoming		Intense test needed
2		Hybrid	Housing	Housing short term calendar	0	0	0	man-days	5		100%	validated	100%	deployed		Intense test needed , Fix max itens length value	Missing loadings, missing UI
2		Hybrid	Housing	Favorite housing list	0	0	0	man-days	5		100%	validated	100%	deployed		Imo this need to be evaluated
3		Hybrid	Visit list	Visit list	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed		Imo this need to be evaluated
3		Hybrid	Visit list	Visit request	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
3		Hybrid	Visit list	Visit edition	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
2		Hybrid	Event list	Event list	0	0	0	man-days	5	Fernando	100%	validated	100%	missing
2		Hybrid	Banking	Banking information	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
2		Hybrid	Banking	Payment method list	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
2		Hybrid	Banking	Payment method creation	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
2		Hybrid	Banking	Payment method edition	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
2		Hybrid	Banking	Payout method list	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
2		Hybrid	Banking	Payout method creation	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
2		Hybrid	Banking	Payout method edition	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
2		Hybrid	Banking	Payment list	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
2		Hybrid	Banking	Payment creation	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed		Bug displaying icon for features with false as a value and not showing their names
2		Hybrid	Banking	Payment confirmation	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
2		Hybrid	Document	Document list	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
2		Hybrid	Document	Document creation	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
2		Hybrid	Donation	Donation creation	0	0	0	man-days	5	Fernando	100%	validated	100%	missing		Slide on housing done, but remains adding the comentary and evaluation on dashboard
2		Hybrid	Donation	Donation edition	0	0	0	man-days	5	Fernando	100%	validated	100%	missing
2		Hybrid	Carbon compensation	Carbon compensation creation	0	0	0	man-days	5	Fernando	100%	validated	100%	missing			Missing verified user, response rate, speaking langages
2		Hybrid	Carbon compensation	Carbon compensation edition	0	0	0	man-days	5		100%	validated	100%	missing			Missing final style
2		Hybrid	Carbon compensation	Carbon compensation information	0	0	0	man-days	5		100%	validated	100%	missing			Missing final style
2		Hybrid	Chat list	Chat list	0	0	0	man-days	5		100%	validated	100%	deployed		Need evaluation
2		Hybrid	Chat	Chat creation	0	0	0	man-days	5		100%	validated	100%	deployed		Need evaluation
2		Hybrid	Chat	Chat edition	0	0	0	man-days	5		100%	validated	100%	deployed
2		Hybrid	Profile	Profile creation	0	0	0	man-days	5		100%	validated	100%	upcoming
2		Hybrid	Housing	Housing overview	0	0	0	man-days	5		70%	upcoming	100%	upcoming
2		Hybrid	Housing	Housing edition	0	0	0	man-days	5	Fernando	50%	upcoming	100%	upcoming		The contract by default is 3 years and you can go from 9 months to 3 years : 9 to 12 months then 1,2 and 3 years By default : 3 years
2		Hybrid	Housing	Housing booking edition	0	0	0	man-days	5	Fernando	50%	upcoming	100%	missing
2		Hybrid	Housing	Housing rules	0	0	0	man-days	1	Fernando	50%	upcoming	100%	missing
2		Hybrid	Onboarding	Onboarding long term location	0	0	0	man-days	5		0%	missing	100%	deployed			Same state as homepage
2		Hybrid	Onboarding	Onboarding long term type list	0	0	0	man-days	5		0%	missing	100%	deployed
2		Hybrid	Onboarding	Onboarding long term budget	0	0	0	man-days	5		0%	missing	100%	deployed
2		Hybrid	Onboarding	Onboarding long term housing list	0	0	0	man-days	5		0%	missing	100%	deployed
2		Hybrid	Home	Home Application	0	0	0	man-days	5		0%	missing	100%	deployed
2		Hybrid	Home	Home Moien	0	0	0	man-days	1	Luís	0%	missing	100%	deployed
2		Hybrid	Home	Home newsletter subscription	0	0	0	man-days	1	Luís	0%	missing	100%	deployed
2		Hybrid	Account	Account statistics	0	0	0	man-days	4	Fernando	0%	missing	100%	deployed
2		Hybrid	Housing	Housing rules edition	0	0	0	man-days	5	Fernando	0%	missing	100%	missing
2		Hybrid	Housing	Housing statistics	0	0	0	man-days	4	Fernando	0%	missing	100%	missing
2		Hybrid	Housing	Housing management	0	0	0	man-days	5	Fernando	0%	missing	100%	missing
2		Hybrid	Housing	Housing calendar	0	0	0	man-days	5		0%	missing	100%	upcoming
2		Hybrid	Housing	Cancellation policy selection	0	0	0	man-days	5		0%	missing	100%	deployed
2		Hybrid	Booking calendar	Booking calendar	0	0	0	man-days	5		0%	missing	100%	missing
2		Hybrid	Booking calendar	Booking list	0	0	0	man-days	5		0%	missing	100%	missing
2		Hybrid	Booking calendar	Booking creation calendar	0	0	0	man-days	5		0%	missing	100%	missing
2		Hybrid	Booking calendar	Booking creation guest count	0	0	0	man-days	5		0%	missing	100%	missing
2		Hybrid	Booking calendar	Booking creation rules	0	0	0	man-days	5		0%	missing	100%	missing
2		Hybrid	Booking calendar	Booking creation payment	0	0	0	man-days	5		0%	missing	100%	missing
2		Hybrid	Booking calendar	Booking creation confirmation	0	0	0	man-days	5		0%	missing	100%	missing
2		Hybrid	Booking calendar	Booking search	0	0	0	man-days	5		0%	missing	100%	missing			This still need to be finish
2		Hybrid	Booking calendar	Booking location filter	0	0	0	man-days	5		0%	missing	100%	missing
2		Hybrid	Booking calendar	Booking short term search filter	0	0	0	man-days	5		0%	missing	100%	missing
2		Hybrid	Booking calendar	Booking dashboard	0	0	0	man-days	5	Fernando	0%	missing	100%	missing
2		Hybrid	Event list	Event creation	0	0	0	man-days	5		0%	missing	100%	missing
2		Hybrid	Notification	Notification edition	0	0	0	man-days	5	Fabiano	0%	missing	100%	deployed
2		Hybrid	Housing	Housing gallery	0	0	0	man-days	5	Fabiano	100%	validated	90%	deployed
2		Hybrid	Housing	Housing gallery edition	0	0	0	man-days	5	Fabiano	70%	upcoming	90%	in progress
2		Hybrid	Profile	Profile edition	0	0	0	man-days	5	Fernando, Luís	100%	validated	100%	upcoming
2		Hybrid	Housing	Housing creation	0	0	0	man-days	1	Fernando	50%	upcoming	100%	in progress
2		Hybrid	Banking	Bill list	0	0	0	man-days	2	Luís	70%	upcoming	70%	in progress
2		Hybrid	Document	Document edition	0	0	0	man-days	5	Fernando	0%	missing	100%	missing
2		Hybrid	Banking	Payment summary	0	0	0	man-days	1	Fernando	100%	missing	100%	in progress
2		Hybrid	Core	Update mobile navbar and profile	0	0	0	man-days	2	Fernando	100%	evaluated	100%	missing
2		Hybrid	Blog	Update privacy policies page	0	0	0	man-days	5	Victor	100%	evaluated	100%	missing
2		Hybrid	Blog	Update legal terms page	0	0	0	man-days	5	Victor	100%	evaluated	100%	missing
2		Hybrid	Housing	Housing Availability	0	0	0	man-days	1	Fernando	0%	missing	100%	missing
2		Hybrid	Housing	Housing Seasonality Price	0	0	0	man-days	3	Luís	0%	missing	50%	missing
2		Hybrid	Housing	Handle image formats	0	0	0	man-days	5		0%	missing	100%	missing
2		Hybrid	Housing	Housing day edition	0	0	0	man-days	1	Luís	0%	missing	20%	missing
2		Hybrid	Booking calendar	Booking creation notification	0	0	0	man-days	3	Fabiano	0%	missing	90%	missing
2		Hybrid	Booking calendar	Fix booking search map	0	0	0	man-days	5	Luís	100%	missing	80%	in progress
2		Hybrid	Rating	Property Rating	0	0	0	man-days	2	Victor	0%	missing	100%	missing
2		Hybrid	Rating	Host rating	0	0	0	man-days	2	Victor	0%	missing	100%	missing
2		Hybrid	Rating	Guest rating	0	0	0	man-days	2	Victor	0%	missing	100%	missing
2	0	Hybrid	Mangopay	Update mangopay API Key	0.125	0.1875	0.25	man-days	1	Fernando	0%	missing	50%	missing
2	0	Hybrid	Mangopay	Update mangopay T&Cs link	0.5	0.75	1	man-days	1	Fabiano	0%	missing	0%	missing
2	0	Hybrid	Mangopay	E-mail notification of new T&Cs	0.5	0.75	1	man-days	1	Fabiano	0%	missing	0%	missing
2	0	Hybrid	Mangopay	Implement wire stream	1	1.5	2	man-days	1	Fernando	0%	missing	70%	missing
2	0	Hybrid	Mangopay	Handle payment fail	0.25	0.375	0.5	man-days	1		0%	missing	70%	missing								0.5
2		Hybrid	Mailing	Improve Beta email template	0	0	0	man-days	1	Luís	0%	missing	50%	missing								0.5
2		Hybrid	Signup	Fix signup repeated number bug	0	0	0	man-days	2	Victor	0%	missing	80%	in progress
2		Hybrid	Mobile	Capacitor setup	0	0	0	man-days	2	Luís	0%	missing	100%	in progress
2		Hybrid	Mobile	Android setup	0	0	0	man-days	5	Luís	0%	missing	50%	in progress
2		Hybrid	Mobile	iOS setup	0	0	0	man-days	5	Luís	0%	missing	0%	missing
2	0	Hybrid	Mobile	Capacitor plugins	1	1.5	2	man-days	5	Luís	0%	missing	0%	missing
3		Hybrid	Housing	Housing long term rental information	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed								0.5
3		Hybrid	Housing	Long term rental request	0	0	0	man-days	5		100%	validated	100%	deployed								0.5
3		Hybrid	Housing	Housing long term edition	0	0	0	man-days	5	Fernando	0%	missing	100%	deployed								0.5
3		Hybrid	Housing	Housing visit availability edition	0	0	0	man-days	5	Fernando	0%	missing	100%	deployed								0.5
3		Hybrid	Booking calendar	Booking long term search filter	0	0	0	man-days	5		0%	missing	100%	missing								0.5
3		Hybrid	Project upgrade	Svelte 5	1	1.5	2	man-days	3	Luís	100%	upcoming	50%	in progress		Missing routing
3		Hybrid	Project upgrade	Typescript	3	4.5	6	man-days	3	Luís	100%	upcoming	30%	in progress
3		Hybrid	Housing	Housing long term rental information	0	0	0	man-days	5	Fernando	100%	validated	100%	deployed
3		Hybrid	Housing	Long term rental request	0	0	0	man-days	5		100%	validated	100%	deployed
3		Hybrid	Housing	Housing long term edition	0	0	0	man-days	5	Fernando	0%	missing	100%	deployed
3		Hybrid	Housing	Housing visit availability edition	0	0	0	man-days	5	Fernando	0%	missing	100%	deployed
3		Hybrid	Booking calendar	Booking long term search filter	0	0	0	man-days	5		0%	missing	100%	missing
3		Hybrid	Housing	Long term period	0.25	0.375	0.5	man-days	5		0%	missing	30%	missing
3		Hybrid	Housing	Long term contract creation	0.5	0.75	1	man-days	5		0%	missing	20%	missing
3		Hybrid	Housing	Long term contract edition	0.5	0.75	1	man-days	5		0%	missing	20%	missing
3		Hybrid	Banking	Automatic payment creation	1	1.5	2	man-days	5	Fernando	0%	missing	0%	in progress
3		Hybrid	Banking	Automatic payment edition	1	1.5	2	man-days	5	Fernando	0%	missing	0%	in progress
3		Hybrid	Subscription	Service subscription edition	0.5	0.75	1	man-days	5		0%	missing	0%	missing
3		Hybrid	FAQ	Help	1	1.5	2	man-days	5	Victor	0%	missing	0%	missing
3		Hybrid	Inventory	Inventory creation	0.5	0.75	1	man-days	5		0%	missing	0%	missing
3		Hybrid	Inventory	Inventory edition	0.25	0.375	0.5	man-days	5		0%	missing	0%	missing
4		Hybrid	Housing	Sublet contract creation	2.5	3.75	5	man-days	5		0%	missing	0%	missing
4		Hybrid	Housing	Sublet contract edition	0.5	0.75	1	man-days	5		0%	missing	0%	missing
5		Hybrid	Chat	Chat translation	1	1.5	2	man-days	5		0%	validated	0%	deployed
6		Hybrid	Connectivity	Travel time	1.5	2.25	3	man-days	1		0%	missing	0%	missing
6		Hybrid	Around	Nearby places	5	7.5	10	man-days	1		0%	missing	0%	missing
6		Hybrid	Around	Nearby criminality	5	7.5	10	man-days	1		0%	missing	0%	missing
6		Hybrid	View	Street view	2	3	4	man-days	1		0%	missing	0%	missing
6		Hybrid	Analytics	Nearby rental prices	3	4.5	6	man-days	1		0%	missing	0%	missing
6		Hybrid	Analytics	Nearby sale prices	5	7.5	10	man-days	1		0%	missing	0%	missing
1		Admin	Dashboard	Dashboard	0	0	0	man-days	1	Luís	100%	validated	100%	in progress
1		Admin	Dashboard	Ratings	0	0	0	man-days	1	Luís	100%	validated	100%	missing
1		Admin	Statistics	Statistics	0	0	0	man-days	1	Luís	100%	validated	100%	in progress
1		Admin	Statistics	Number of users registered	0	0	0	man-days	1	Luís	100%	validated	100%	tested
1		Admin	Entities lists and forms	Notification	0	0	0	man-days	1		100%	validated	100%	missing
1		Admin	Entities lists and forms	Toolbar search and filter	0	0	0	man-days	1	Luís	100%	validated	100%	in progress
1		Admin	Settings	Users roles permissions	0	0	0	man-days	1	Fabiano	100%	upcoming	100%	missing
1		Admin	Settings	Article blocks	0	0	0	man-days	1	Luís	100%	validated	100%	in progress
1		Admin	Exploiting	Remove add buttons	0	0	0	man-days	2	Fabiano	100%	validated	100%	deployed
1		Admin	Exploiting	Document actions	0	0	0	man-days	2	Fabiano	100%	validated	100%	in progress
1		Admin	Admin	Page title	0	0	0	man-days	3		100%	validated	100%	in progress
1		Admin	Admin	Toolbar modal	0	0	0	man-days	2		100%	evaluated	100%	in progress
1		Admin	Core	Login page	0	0	0	man-days	1	Fabiano, Luís	0%	missing	100%	deployed
1		Admin	Core	Admin home	0	0	0	man-days	1	Fabiano	0%	missing	100%	deployed		Sum of them in the period (day/ week/ month/ year)
1		Admin	Core	Admin article list	0	0	0	man-days	1	Fabiano, Luís	0%	missing	100%	deployed
1		Admin	Core	Admin article edit	0	0	0	man-days	1	Fabiano, Luís	0%	missing	100%	deployed
1		Admin	Core	Admin block list	0	0	0	man-days	1	Fabiano, Luís	0%	missing	100%	deployed
1		Admin	Core	Admin block edit	0	0	0	man-days	1	Fabiano, Luís	0%	missing	100%	in progress
1		Admin	Connection	Email account connection	0	0	0	man-days	1		0%	missing	100%	deployed
1		Admin	Statistics	Export data to CSV	0	0	0	man-days	1	Luís	0%	missing	100%	tested
1		Admin	Entities lists and forms	Bed list	0	0	0	man-days	1	Luís	0%	upcoming	100%	in progress
1		Admin	Entities lists and forms	Bed edition	0	0	0	man-days	1	Luís	0%	upcoming	100%	in progress
1		Admin	Entities lists and forms	Cancellation policy list	0	0	0	man-days	1	Fernando	0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Cancellation policy edition	0	0	0	man-days	1	Fernando	0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Document type list	0	0	0	man-days	1	Fernando	0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Document type edition	0	0	0	man-days	1	Fernando	0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Energy Diagnosis list	0	0	0	man-days	1		0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Energy Diagnosis edition	0	0	0	man-days	1		0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Housing list	0	0	0	man-days	1		0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Housing edition	0	0	0	man-days	1		0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Image list	0	0	0	man-days	1		0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Image edition	0	0	0	man-days	1		0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Message list	0	0	0	man-days	1		0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Message edition	0	0	0	man-days	1		0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Notification permission list	0	0	0	man-days	1		0%	upcoming	100%	missing
1		Admin	Entities lists and forms	Notification permission edition	0	0	0	man-days	1		0%	upcoming	100%	missing
1		Admin	Entities lists and forms	Payment list	0	0	0	man-days	1		0%	upcoming	100%	missing
1		Admin	Entities lists and forms	Payment edition	0	0	0	man-days	1		0%	upcoming	100%	missing
1		Admin	Entities lists and forms	Payment method list	0	0	0	man-days	1		0%	upcoming	100%	missing
1		Admin	Entities lists and forms	Payment method edition	0	0	0	man-days	1		0%	upcoming	100%	missing
1		Admin	Entities lists and forms	Payout list	0	0	0	man-days	1		0%	upcoming	100%	missing
1		Admin	Entities lists and forms	Payout edition	0	0	0	man-days	1		0%	upcoming	100%	missing
1		Admin	Entities lists and forms	Payout method list	0	0	0	man-days	1		0%	upcoming	100%	missing
1		Admin	Entities lists and forms	Payout method edition	0	0	0	man-days	1		0%	upcoming	100%	missing
1		Admin	Entities lists and forms	Space list	0	0	0	man-days	1		0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Space edition	0	0	0	man-days	1		0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Text list	0	0	0	man-days	1		0%	upcoming	100%	missing
1		Admin	Entities lists and forms	Text edition	0	0	0	man-days	1		0%	upcoming	100%	missing
1		Admin	Entities lists and forms	User list	0	0	0	man-days	1		0%	upcoming	100%	missing
1		Admin	Entities lists and forms	User edition	0	0	0	man-days	1		0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Validation status list	0	0	0	man-days	1		0%	upcoming	100%	deployed
1		Admin	Entities lists and forms	Validation status edition	0	0	0	man-days	1		0%	upcoming	100%	deployed
1		Admin	Admin	Section	0	0	0	man-days	1	Luís	0%	upcoming	100%	missing
1		Admin	Admin	Permissions	0	0	0	man-days	3		0%	missing	100%	deployed
1		Admin	Admin	Back/ cancel alerts	0	0	0	man-days	2	Victor	100%	evaluated	100%	in progress
1		Admin	Admin	Box shadow	0	0	0	man-days	3	Victor	100%	validated	100%	in progress
1		Admin	Settings	Add items	0	0	0	man-days	2	Fabiano	100%	validated	100%	missing
1		Admin	Exploiting	Edit items	0	0	0	man-days	2	Fabiano	100%	validated	100%	in progress
2		Admin	Document	Document upload	0	0	0	man-days	1		0%	upcoming	100%	deployed
2		Admin	Document	Document removal	0	0	0	man-days	1		0%	upcoming	100%	deployed
2		Admin	Image	Image upload	0	0	0	man-days	1		0%	upcoming	100%	deployed
2		Admin	Image	Image removal	0	0	0	man-days	1		0%	upcoming	100%	deployed
2		Admin	Entities lists and forms	Bill list	0	0	0	man-days	1		0%	upcoming	100%	missing
2		Admin	Entities lists and forms	Bill edition	0	0	0	man-days	1		0%	upcoming	100%	missing
2		Admin	Entities lists and forms	Bill line list	0	0	0	man-days	1		0%	upcoming	100%	missing
2		Admin	Entities lists and forms	Bill line edition	0	0	0	man-days	1		0%	upcoming	100%	missing
2		Admin	Entities lists and forms	Rental announcement list	0	0	0	man-days	1		0%	upcoming	100%	deployed
2		Admin	Entities lists and forms	Rental booking list	0	0	0	man-days	1		0%	upcoming	100%	missing
2		Admin	Entities lists and forms	Rental booking edition	0	0	0	man-days	1		0%	upcoming	100%	missing
2		Admin	Entities lists and forms	Rental cost list	0	0	0	man-days	1		0%	upcoming	100%	deployed
2		Admin	Entities lists and forms	Rental review list	0	0	0	man-days	1		0%	upcoming	100%	missing
2		Admin	Entities lists and forms	Rental review edition	0	0	0	man-days	1		0%	upcoming	100%	missing
2		Admin	Entities lists and forms	User review list	0	0	0	man-days	1		0%	upcoming	100%	missing
2		Admin	Entities lists and forms	User review edition	0	0	0	man-days	1		0%	upcoming	100%	missing
2		Admin	Entities lists and forms	Rental day list	0	0	0	man-days	1	Fabiano	0%	upcoming	80%	in progress
2		Admin	Dashboard	Payment anomalies	0	0	0	man-days	1	Luís	100%	validated	80%	in progress
2		Admin	Entities lists and forms	Rental announcement edition	0	0	0	man-days	1	Fabiano	0%	upcoming	50%	in progress
2		Admin	Dashboard	Search tickets	0	0	0	man-days	1	Fabiano	100%	validated	40%	in progress
2		Admin	Entities lists and forms	Rental announcement import	0	0	0	man-days	1	Fabiano	0%	upcoming	20%	in progress
2		Admin	Exploiting	Comparison filters	0	0	0	man-days	2	Fabiano	100%	validated	100%	missing
2		Admin	Statistics	Number of ads viewed	0	0	0	man-days	3	Fabiano	100%	evaluated	0%	missing
2		Admin	Statistics	Turnover view	0	0	0	man-days	3	Fabiano	100%	evaluated	0%	missing
2	1	Admin	Mailing	Implement mailchimp features on Admin	1	1.5	2	man-days	1	Fabiano	0%	missing	50%	missing								0.5
3		Admin	Entities lists and forms	Service list	1	1.5	2	man-days	1		0%	upcoming	0%	missing
3		Admin	Entities lists and forms	Service edition	0.5	0.75	1	man-days	1		0%	upcoming	0%	missing
3		Admin	Entities lists and forms	Subscription list	0.75	1.125	1.5	man-days	1		0%	upcoming	50%	in progress
3		Admin	Entities lists and forms	Subscription edition	0.25	0.375	0.5	man-days	1		0%	upcoming	50%	in progress
3		Admin	Entities lists and forms	Automatic payment list	0.25	0.375	0.5	man-days	1		0%	upcoming	0%	missing
3		Admin	Entities lists and forms	Automatic payment edition	0.25	0.375	0.5	man-days	1		0%	upcoming	0%	missing
2		Admin	Entities lists and forms	Rental cost edition	0	0	0	man-days	1		0%	upcoming	100%	missing
2		Admin	Entities lists and forms	Rental day edition	0	0	0	man-days	1		0%	upcoming	100%	missing
3		Admin	Entities lists and forms	Inventory list	0	0	0	man-days	1	Fabiano	0%	upcoming	100%	deployed		Administrator : / - Access to everything; / - Possibility to modify everything; / - No possibility to erase; / BO Senior: / - not Access to emails/text management / BO: / - same as BO senior + not access to abonnement / - Access to blog only in lecture / Gest/host: / - no access to admin / Agencies: / - Access to users/abonnement/stats only for the users linkek to them
3		Admin	Entities lists and forms	Invoice list	0	0	0	man-days	1		0%	upcoming	100%	missing
3		Admin	Entities lists and forms	Invoice edition	0	0	0	man-days	1		0%	upcoming	100%	missing
3		Admin	Entities lists and forms	Lease contract list	0	0	0	man-days	1		0%	upcoming	100%	missing
3		Admin	Entities lists and forms	Lease contract edition	0	0	0	man-days	1		0%	upcoming	100%	missing
3		Admin	Dashboard	Schedule	0.375	0.5625	0.75	man-days	1	Luís	0%	validated	70%	in progress
3		Admin	Entities lists and forms	Document template list	1.5	2.25	3	man-days	1		0%	upcoming	20%	missing
3		Admin	Entities lists and forms	Document template edition	0.5	0.75	1	man-days	1		0%	upcoming	20%	missing
3		Admin	Admin	Header menu	0.125	0.1875	0.25	man-days	5	Fernando	50%	upcoming	0%	missing
3		Admin	Entities lists and forms	Inventory edition	0.5	0.75	1	man-days	1		0%	upcoming	0%	missing
3		Admin	Entities lists and forms	Appointment list	0	0	0	man-days	1		0%	upcoming	100%	deployed
3		Admin	Entities lists and forms	Appointment edition	0	0	0	man-days	1		0%	upcoming	100%	deployed
4		Admin	Entities lists and forms	Sublet contract list	0.25	0.375	0.5	man-days	1		0%	upcoming	0%	missing
4		Admin	Entities lists and forms	Sublet contract edition	0.375	0.5625	0.75	man-days	1		0%	upcoming	0%	missing
6		Admin	Entities lists and forms	Criminality data geostatistics import	5	7.5	10	man-days	1		0%	missing	0%	missing
6		Admin	Entities lists and forms	Sale prices geostatistics import	5	7.5	10	man-days	1		0%	missing	0%	missing
6		Admin	Entities lists and forms	Rental prices geostatistics generation	3	4.5	6	man-days	1		0%	missing	0%	missing

			Total		59	88.5	118	man-days	1.26	1.90	2.53	months

Values
1	0								0	Eric		missing		missing
2	1								1	Fabiano		upcoming		upcoming
3	2								2	Fernando		in progress		in progress
4	3								3	Luís		evaluated		tested
5	4								4	Jefferson		validated		deployed
6									5	Victor

Phases					Minimum	Medium	Maximum	Unit	Minimum	Medium	Maximum	Unit	Sum	Min. Date	Max. Date	Description
1					0	0	0	man-days	0.00	0.00	0.00	months	0.00	13/01/2025	27/01/2025	Limited website with home page and blog articles to explain the Moien concept
2					4.375	6.5625	8.75	man-days	0.09	0.14	0.19	months	0.19	18/01/2025	01/02/2025	Website and mobile application with short term workflow
3					15.5	23.25	31	man-days	0.33	0.50	0.66	months	0.85	07/02/2025	21/02/2025	Website and mobile application with short term and long term workflow
4					3.625	5.4375	7.25	man-days	0.08	0.12	0.16	months	1.01	12/02/2025	26/02/2025	Website and mobile application with short term, long term and sublet workflow
5					1	1.5	2	man-days	0.02	0.03	0.04	months	1.05	13/02/2025	27/02/2025	Website and mobile application with additional features (chat translation, etc)
6					34.5	51.75	69	man-days	0.74	1.11	1.48	months	2.53	30/03/2025	13/04/2025	Website and mobile application with proximity features (travel times, places, prices, etc)

				Total	59	88.5	118	man-days	1.26	1.90	2.53	months

Sprint					Minimum	Medium	Maximum	Unit	Start Date	Deploy Date
0					3.375	5.0625	6.75	man-days	21/06/2024	27/06/2024
1					1	1.5	2	man-days	28/06/2024	04/07/2024
2					0	0	0	man-days	05/07/2024	11/07/2024
3					0	0	0	man-days	12/07/2024	18/07/2024
4					0	0	0	man-days	19/07/2024	25/07/2024

Groups
			About		0	0	0	man-days	0.00	0.00	0.00	months
			Account		0	0	0	man-days	0.00	0.00	0.00	months
			Admin		0.125	0.1875	0.25	man-days	0.00	0.00	0.01	months
			Analytics		8	12	16	man-days	0.17	0.26	0.34	months
			Around		10	15	20	man-days	0.21	0.32	0.43	months
			Banking		2	3	4	man-days	0.04	0.06	0.09	months
			Blog		0	0	0	man-days	0.00	0.00	0.00	months
			Booking calendar		0	0	0	man-days	0.00	0.00	0.00	months
			Carbon compensation		0	0	0	man-days	0.00	0.00	0.00	months
			Chat		1	1.5	2	man-days	0.02	0.03	0.04	months
			Chat list		0	0	0	man-days	0.00	0.00	0.00	months
			Connection		0	0	0	man-days	0.00	0.00	0.00	months
			Connectivity		1.5	2.25	3	man-days	0.03	0.05	0.06	months
			Core		0	0	0	man-days	0.00	0.00	0.00	months
			Dashboard		0.375	0.5625	0.75	man-days	0.01	0.01	0.02	months
			Document		0	0	0	man-days	0.00	0.00	0.00	months
			Donation		0	0	0	man-days	0.00	0.00	0.00	months
			Entities lists and forms		19.125	28.6875	38.25	man-days	0.41	0.61	0.82	months
			Event list		0	0	0	man-days	0.00	0.00	0.00	months
			Exploiting		0	0	0	man-days	0.00	0.00	0.00	months
			FAQ		1	1.5	2	man-days	0.02	0.03	0.04	months
			Home		0	0	0	man-days	0.00	0.00	0.00	months
			Housing		4.25	6.375	8.5	man-days	0.09	0.14	0.18	months
			Image		0	0	0	man-days	0.00	0.00	0.00	months
			Inventory		0.75	1.125	1.5	man-days	0.02	0.02	0.03	months
			Mangopay		2.375	3.5625	4.75	man-days	0.05	0.08	0.10	months
			Notification		0	0	0	man-days	0.00	0.00	0.00	months
			Onboarding		0	0	0	man-days	0.00	0.00	0.00	months
			Profile		0	0	0	man-days	0.00	0.00	0.00	months
			Rating		0	0	0	man-days	0.00	0.00	0.00	months
			Settings		0	0	0	man-days	0.00	0.00	0.00	months
			Start		0	0	0	man-days	0.00	0.00	0.00	months
			Statistics		0	0	0	man-days	0.00	0.00	0.00	months
			Subscription		0.5	0.75	1	man-days	0.01	0.02	0.02	months
			View		2	3	4	man-days	0.04	0.06	0.09	months
			Visit list		0	0	0	man-days	0.00	0.00	0.00	months

				Total	53	79.5	106	man-days	1.14	1.70	2.27	months

## Configuration
Name	Value
Team velocity	2.5